## Summary
Group | Team | Start | Nov Total | Color | Opportunities for Improvement |  | Group | Team | Start | Nov Total | Color
|  | -4.5 | 9.5 |  |  | Direct Ongoing Contact
2
10.5
11
|  |  | 12 |  |  | Assessed through interviews
11
10.5
11.5
11.5
8
8
11.5
|  |  | 4 |  |  |  | Pre-Forming | Forming | Norming | Performing
|  | -5 | 1 |  |  |  | 0-3 | 4-5 | 6-11 | 12-13
|  | 4.5 | 12.5
|  | -7 | 4.5
?

## Master
| D | I | R | Category | Pre-forming | Forming | Norming | Performing | Questions to guide conversation
5.3333 | 6 | 6 | 4 | Transparency – Team is clear about what is to be delivered and understands how those items relate to product roadmap |  | Product Manager has a clear view into all the work the team has in the backlog and the status of each of the features prioritized in the backlog | The scrum teams provide quarterly objectives (based on features presented) to business owner and business owner assigns business value to those objectives | Each sprint has goals that align to the product roadmap enabling the entire organization to easily understand how each sprint fits into the big picture | -Who is the product Manager? -Who is the product Owner? -How frequently do they talk? -do you guys do quarterly planning? If so business objectives? -do you typically theme your sprints?
4.6667 | 2 | 7 | 5 | Communication -Everyone is clear about the product vision and can see how their day to day activities impact it's realization |  | Product Manager delivers product vision and roadmap presentation to team quarterly | Team understands how individual stories relate to the strategic vision. | Team understands user and buyer personas and how the work they do affects that audience. | -Do teams know the product vision and roadmap? -In general do the team members know how their day to day impacts the vision? -Do teams have a sense of buyer personas and impacts to those?
7.6667 | 7 | 8 | 8 | Business Engagement - Product Management & Development function well together and align around a common objective |  | Product Owner maintains backlog and attends all ceremonies | Product Manager and Product Owner work regularly to define Epics and Features so Product Owner can break those into stories | Product Manager and Product Owner are engaged in necessary scrum ceremonies. Product Manager presents feature demos and release planning | -How do the productmanager and product owner work together?
4.6667 | 8 | 3 | 3 | Predictability- Work the team is able to produce is known and trusted. |  | Teams deliver on less than 80% of commitments and do not have a steady velocity | Teams have stable velocity and deliver on less than 80% or greater than 100% of commitments | Teams have stable velocity and deliver on 80-100% of commitments | -What tool do you use to track work?
5 | 9 | 4 | 2 | Prioritization - Clear, objective priorities for the work that is to be done |  | Team has one backlog | There is a prioritized allocation for backlog (e.g. 60% capex, 40% opex) | Quantified business value for each epic drives execution priority. Team tracks value post-delivery and continually reviews effectiveness. | -Does all of your work come from a single backlog? -How is that prioritized?
9.6667 | 10 | 10 | 9 | Focus - Teams limit distractions and concentrate in a focused direction |  | Dev, QA are dedicated to a single team. PO & Scrum Master are responsible for a maximum of 1-2 teams. | Team members dedicate 60% of their effort in a sprint toward a clearly related set of epics | Team members dedicate 80+% of their effort in a sprint delivering a clearly related set of features | -Are team members generally dedicated to a single team? -Who makes up a team? -What categories of work do you typically do in a sprint?
6.6667 | 1 | 9 | 10 | Technical Practices - The way we complete stories reduces technical overhead |  | Automated regression tests run regularly | TDD & Continuous Integration | Continuous Deployment | -Is QA automated? -How frequently do you integrate code? -How frequently can you deploy?
4.6667 | 5 | 2 | 7 | Dependancy Management - Teams are able to effectively coordinate cross functional dependancies |  | ScrumMaster works informally with other teams to align inputs and outputs | Regularly scheduled Scrum of Scrums to align dependancies | Quarterly Release Planning event with participation from all dependant teams | -How do you deal with dependancies from other teams?
5 | 4 | 5 | 6 | Funding - Teams are funded in ways that limit disruption and enable highest value work first |  | Constant project level funding allows teams to remain intact | Teams are funded with a yearly business case and are able to select highest value work throughout the year | Program is funded with a yearly business case able to select highest value work throughout the year | -How is the team funded? Project or larger annual business case?
|  |  |  | Column totals | 0 |  |  | 0
[5 empty] | 0 |  | 0 | 0 | 0
[5 empty] | Pre-Forming | Forming | Norming | Performing
Maturity Level
Note on G5: Danny Presten: Assumes stories include dev and QA tasks